Practical No-03

Aim: Estimation of Project matrix and design Gnatt chart

Problem Statement: AI Stock Analyzer

A Project Estimation Matrix is a structured format used to estimate time, effort, resources, and cost for each module/task of a project. It helps in planning and tracking.

| Task ID | Task Name | Assigned To | Estimated Hours | Actual Hours | Start Date | End Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| T1 | Requirement Gathering | Atharva | 10 hrs | 14 hrs | 20-Aug-25 | 23-Aug-25 | Completed |
| T2 | UI Design | Designer | 15 hrs | 14 hrs | 24-Aug-25 | 27-Aug-25 | In Progress |
| T3 | Backend Development | Developer | 25 hrs | - | 28-Aug-25 | 5-Sept-25 | Pending |

Example of a Project Estimation Matrix

| Component | Description | Estimation Technique | Estimation (Example) |
| --- | --- | --- | --- |
| Effort | Number of person-hours required | Function Point Analysis | 1,000 person-hours |
| Time (Duration) | Calendar time for project completion | PERT/CPM | 3 months |
| Cost | Estimated budget for project | Bottom-Up Estimation | $50,000 |
| Size | Size of the software | Function Points | 300 function points |
| Resources | Number of developers, testers, etc. required | Expert Judgment | 4 developers, 2 testers |
| Risk | Contingency for identified risks | Risk Analysis (Qualitative) | 10% buffer on time/cost |

Example: Library Management System (Mini Project)

| Task ID | Module | Est. Hours | Resources | Complexity | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | Login/Authentication | 6 hrs | Developer A | Low | Simple form |
| 2 | Book Search | 10 hrs | Developer B | Medium | Uses database |
| 3 | Book Issue/Return | 15 hrs | Developer A, B | High | With logic |
| 4 | Admin Dashboard | 8 hrs | Developer A | Medium | Stats, graphs |

| Task ID | Module | Est. Hours | Resources | Complexity | Hourly Rate (INR) | Estimated Cost (INR) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Login/Authentication | 6 | Developer A | Low | 600 | 3600 |
| 2 | Book Search | 10 | Developer B | Medium | 600 | 6000 |
| 3 | Book Issue/Return | 15 | Developer A, B | High | 600 | 9000 |
| 4 | Admin Dashboard | 8 | Developer A | Medium | 600 | 4800 |
|  |  |  |  | Total Cost |  |  |

2. Gantt Chart Design

Steps to Design a Gantt Chart

A Gantt chart is a bar chart that visually represents the schedule of a project, showing tasks over time. Here's how to design one step-by-step:

Step-by-Step Process to Design a Gantt Chart

Step 1: Identify Project Tasks

List all the tasks or modules required to complete the project.

- Example:

  - Requirement Gathering

  - UI Design

  - Development

  - Testing

  - Deployment

Step 2: Determine Task Duration

Estimate how long each task will take (in days or hours).

- Example:

  - UI Design – 3 days

  - Development – 6 days

Step 3: Set Start and End Dates

Assign start and end dates for each task based on estimated duration and task dependencies.

Step 4: Identify Task Dependencies

Determine which tasks must be completed before others begin.

- Example:

  - Development starts after UI Design

  - Testing starts after Development

Step 5: Create a Table

Prepare a basic table structure like this:

| Task Name | Start Date | Duration | End Date | Progress |
| --- | --- | --- | --- | --- |
| UI Design | 01-Aug-25 | 3 days | 03-Aug-25 | 100% |
| Backend Development | 04-Aug-25 | 6 days | 09-Aug-25 | 60% |

Step 6: Plot on a Timeline (Bar Chart)

Use a horizontal bar chart to represent tasks:

- X-axis: Dates or time period

- Y-axis: Task names

- Draw bars from start to end date of each task

Step 7: Add Details

- Color Code: Use different colors for “Completed”, “In Progress”, and “Planned”

- Milestones: Mark important checkpoints

- Progress Indicator: Show how much of each task is completed

Gantt Chart (Library Management System Project)

Conclusion:

This practical reinforces the significance of software engineering project management techniques. Understanding and applying cost estimation matrices and Gantt charts are essential skills for ensuring that a project is delivered on time, within budget, and with optimal use of resources. These tools also enhance project visibility, risk management, and stakeholder communication.